Project handbook

Wetterstation

001

Version 13

Project manager: Matthias Brückl

Date: 13/05/26

Content

1	Project plans	6

1.1	Project Assignment	6

1.2	Project Objectives (objectives, non-objectives)	8

1.3	Description of Pre- and Post Project Phase	9

1.4	Project Environment Analysis	10

1.5	Relationship to Other Projects and the Organisations´s Strategy	11

1.6	Project Organisation Chart	12

1.7	Plan of Objects of Consideration of the Project	13

1.8	Work Breakdown Structure (WBS)	14

1.9	Project Work-Package Specification	15

1.10	Project Responsibility Matrix	19

1.11	Milestoneplan	21

1.12	Project Bar Chart	22

1.13	Resource Plan	23

1.14	Project Cost Plan	24

1.15	Project Communication	25

1.16	Project „Rules“	26

1.17	Project Risk Analysis	27

1.18	Project Documentation	28

2	Project Start	29

2.1	Minutes– Project Start	29

3	Project Co-ordination	30

3.1	Approval of Work-packages	30

3.2	Minutes – Project Co-ordination	30

4	Project Controlling	31

4.1	Project Status Report	31

4.2	Project Status Report	32

4.3	Project Status Report	33

4.4	Project Status Report	34

4.5	Project Status Report	35

4.6	Project Status Report	36

4.7	Project Status Report	37

4.8	Project Status Report	38

4.9	Additional Project Status Reports	39

4.10	Minutes – Project controlling	39

5	Project Close Down	40

5.1	Project Close Down Report	40

5.2	Minutes – Project Close Down	41

Document versions

| Versionno. | Date | Change | Author |
| --- | --- | --- | --- |
| 1 | 24.11.25 | Start | Brückl M. |
| 2 | 28.11.25 | Objectives and project organization completed | Aistleitner D. |
| 3 | 29.11.25 | Completion till 1.5 | Bergbauer K. |
| 4 | 30.11.25 | Completion till 1.9 | Bergbauer K. Aistleitner D. |
| 5 | 01.12.25 | Updateing 1.4 and 1.9 | Aistleitner D. |
| 6 | 02.12.25 | Finishing the Parts for Project Handbook Part 1 up to 1.10 | Brückl M. |
| 7 | 24.01.26 | Optimizing project environment graphic | Bergbauer K. |
| 8 | 25.01.26 | Update according the feedback | Brückl M. |
| 9 | 01.02.26 | Update according the feedback and complete 1.13 to 2 | Brückl M. |
| 10 | 02.02.26 | First Weekly Report | Bergbauer K. |
| 11 | 16.02.26 | Weekly Report + Update according the feedback | Brückl M. |
| 12 | 11.03.26 | Weekly Report + Update according the feedback | Aistleitner D. |
| 13 | 18.03.26 | Write next Weekly Report | Brückl M. |
| 14 | 24.03.26 | Weekly Report + Update according the feedback + new WBS | Bergbauer K. |
| 15 | 14.04.26 | Write next Progress Report | Aistleitner D. |
| 16 | 29.04.26 | Weekly Report + Update according the feedback | Brückl M. |
| 17 | 13.05.26 | Weekly Report | Bergbauer K. |

Distribution list

| Name | Organisational Unit | Role in project | Telephone | E-mail |
| --- | --- | --- | --- | --- |
| Brückl Matthias | Project Manager | Backend Developer | 0664 994484299 | Matthias.brueckl@htl- wels.at |
| Berbauer Klaus | Project Team Member | Hardware and 3d Modelling | 0677 641591985 | Daniel.aistleitner@htl- wels.at |
| Aistleitner Daniel | Project Team Member | Frontend Developer | 0660 90940434 | Klaus.bergbauer@htl- wels.at |
| HTl-Wels | Project Owner |  | 0664123456789 | office@htl-wels.at |
| Smart-Wand | Stakeholder | Help with optimizing | 0681 108468979 | Paul.auer@htl-wels.at |
| Smart Flowerpot | Stakeholder | Help with optimizing | 0677 632238199 | Thomas.toferer@htl-wels.at |

# Project plans

## Project Assignment

| Wetterstation 001 | PROJECT- ASSIGNMENT |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Project start event: - Submission of the Project shandbook |  | Project start date: - 12.01.2026 |  |  |  |  |
| project close down event in terms of content: - Active usage of the weatherstation Formal project close down event: - Handing the weatherstation over to the teacher |  | Project close down dates: - 10.06.2026 |  |  |  |  |
| Project objectives: - Functioning weather station - Energy-independent power supply - Web based data analyse - Minimalist Case |  | Non-objectives: - No complex data processing - No guarantee of absolute accuracy of the - measurement data. - No use of cloud storage (e.g., Google Drive, AWS, - Azure). - No failover protection through redundant hardware - components. - No remote control |  |  |  |  |
| Main tasks (Project phases): - Conding Frontend - Read out the date of the sensors - Coding a small database - Coding APIs - 3d modelling the Case |  | Project resources and costs*: |  |  |  |  |
|  |  |  | resource/type of cost | unit | Costs (€) |  |
|  |  |  | Raspberry Pi 2w / A BME280 / A DHT22 / A VEML6075 / A Breadboard / A PETG-Filament / A | 1 1 1 1 1 3 | 30€ 5€ 8€ 10€ 5€ 45€ |  |
| Project owner: - Htl Wels |  | Project manager: - Brückl Matthias |  |  |  |  |
| Project team members: - Aistleitner Daniel - Bergbauer Klaus |  |  |  |  |  |  |
| HTL Wels, (Project owner) Matthias Brückl (Project manager) |  |  |  |  |  |  |

* Possible categories of total Project budget:

Category A: up to 0,3 million Euro

Category B: up to 1 million Euro

Category C: up to 10 million Euro

Category D: more than 10 million Euro

## Project Objectives (objectives, non-objectives)

| Wetterstation 001 |  | PROJECT OBJECTIVES |  |  |
| --- | --- | --- | --- | --- |
| Type of objective | Project objectives |  | Adjusted project objectives as of... |  |
| objectives: - Main objectives - Additional objectives | - Readout following sensors: - UV sensor - Temperature sensor - Air pressure sensor - Humidity sensor - Anempmeter for windspeed - Web based data analyse - Minimalist Case |  |  |  |
| Non-objectives | - No complex data processing - No guarantee of absolute accuracy of the measurement data. - No use of cloud storage (e.g., Google Drive, AWS, Azure). - No failover protection through redundant hardware components. - No remote control |  | - If there is enough time left before end of mai this objective could be transformed into an additional object. |  |

## Description of Pre- and Post Project Phase

| Wetterstation 001 |  | DESCRIPTION OF PRE- AND POST- PROJECT PHASE |  |
| --- | --- | --- | --- |
| - Pre-project phase |  |  |  |
|  | What triggered the project? - An assignment for ITP in school - The idea of the project was given to us by Brückl’s mom - She wants to know the exact temperature in her garden |  |  |
|  | Relevant documents for the project („Minutes“, … ONLY documents and no content necessary) - Weatherstation_Goals.docx - Materiallist.docx - Wetterstation_Pflichtenheft.docx - Protokoll.docx |  |  |
|  | Experience from similar projects - Groupwork SEW in second class (Aistleitner/Brückl/Bergbauer) - Built a react Website (Brückl) |  |  |
| - Post-project phase |  |  |  |
|  | What will happen after the project has ended? (follow-up activities, further projects, …)? - Project will be presented on the “Open House Day” at School |  |  |

## Project Environment Analysis

| Wetterstation 001 | PROJECT ENVIRONMENT GRAPHIC |  |
| --- | --- | --- |

| Wetterstation 001 |  | PROJECT ENVIRONMENT TABLE |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Environment | Relationship (potential/conflict) |  | Measures |  | Who / when PSP Code |
| Stakeholder | potential |  | Can help us to optimize our project |  | HTL-Wels/ Professors |
| Other Projects | potential |  | can help each other |  | Smart-Flowerpot/ Smart-Wand |
| Technology | potential |  | help us to implement it as we envision it |  | Database/Coding languages/ Raspberry Pi |
| Other Projects | conflict |  | Are competition |  | Indoor Wetterstation |

## Relationship to Other Projects and
the Organisations´s Strategy

| Wetterstation 001 |  | RELATIONSHIP TO OTHER PROJECTS |  |  |
| --- | --- | --- | --- | --- |
| Programs/ Projects/ | Relationship (potential/conflict) |  | Sanctions | Who / when WBS Code |
| Indoor- Wetterstation | Conflict |  | Competition | Paul Gnadlinger; Nicolas Goiginger |
| Smarter Blumentopf | Potential |  | Support with Know-how | Paul Auer |
| Smart-Wand | Potential |  | Support with Know-how | Thomas Toferer |

| Wetterstation 001 |  | CONNECTION TO THE ORGANISATION´S STRATEGY |  |
| --- | --- | --- | --- |
| Strategy | Description of connection/relationship |  |  |
| - | - |  |  |

## Project Organisation Chart

| Wetterstation 001 |  | PROJECT- ORGANISATION |  |  |
| --- | --- | --- | --- | --- |
| Role in Project | Field of duties/Skills |  | Name |  |
| Project owner | Financial providence |  | HTL Wels |  |
| Project manager | Backend development |  | Matthias Brückl |  |
| Project team members | 1. Frontend development 2. Hardware and 3d Modelling |  | 1) Daniel Aistleitner 2) Klaus Bergbauer |  |
| Project members |  |  |  |  |

## Plan of Objects of Consideration of the Project

| Wetterstation 001 | PLAN OF OBJECTS OF CONSIDERATION |  |
| --- | --- | --- |

## Work Breakdown Structure (WBS)

## Project Work-Package Specification

| Wetterstation 001 |  | PROJECT WORK-PACKAGE SPECIFICATION |  |
| --- | --- | --- | --- |
| 1.1 Setup a Folder Structure | WP Content (What shall be done?) - Think about a clear folder structure |  |  |
|  | WP Result (What is achieved after WP was finished?) - Have a clear folder structure |  |  |
|  | Progress Measurement (How is progress measured?) - Every File has his right place |  |  |
| 1.2 Workout Project Requirements | WP Content (What shall be done?) - Think about the Project Requirements |  |  |
|  | WP Result (What is achieved after WP was finished?) - Have a clear vision of the Project |  |  |
|  | Progress Measurement (How is progress measured?) - The Requirements willincrease |  |  |
| 1.3 Workout Project Handbook section 1-3 | WP Content (What shall be done?) - Filling the Project-Handbook |  |  |
|  | WP Result (What is achieved after WP was finished?) - The sections 1-3 have the right entries |  |  |
|  | Progress Measurement (How is progress measured?) - The Project-Handbook are filling |  |  |
| 1.4 Workout Project Handbook section 4-5 | WP Content (What shall be done?) - Filling the Project-Handbook section 4-5 |  |  |
|  | WP Result (What is achieved after WP was finished?) - The sections 4-5 have the right entries |  |  |
|  | Progress Measurement (How is progress measured?) - The Project-Handbook are filling |  |  |
| 1.5 Workout Project Specification Section | WP Content (What shall be done?) - Filling the Project Specification |  |  |
|  | WP Result (What is achieved after WP was finished?) - Have a clear Project Specification, which has the right entries |  |  |
|  | Progress Measurement (How is progress measured?) - The Project Specification are filling |  |  |
| 2.1 Raspberry activation | WP Content (What shall be done?) - Setting up the raspberry |  |  |
|  | WP Result (What is achieved after WP was finished?) - Make the raspberry useable |  |  |
|  | Progress Measurement (How is progress measured?) - If raspberry is ready |  |  |
| 2.2 Sensor implementation | WP Content (What shall be done?) - Sensor implementing |  |  |
|  | WP Result (What is achieved after WP was finished?) - Make the raspberry useable for the sensors |  |  |
|  | Progress Measurement (How is progress measured?) - If raspberry is ready |  |  |
| 2.3 Write Sensor Scripts | WP Content (What shall be done?) - Make the data from the sensors usable |  |  |
|  | WP Result (What is achieved after WP was finished?) - The data is displayed in the terminal |  |  |
|  | Progress Measurement (How is progress measured?) - Scripts are finished for each sensors |  |  |
| 2.4 Case modeling | WP Content (What shall be done?) - Modeling the case of the weather station |  |  |
|  | WP Result (What is achieved after WP was finished?) - Have a file to print |  |  |
|  | Progress Measurement (How is progress measured?) - Having a promising model |  |  |
| 2.5 Print Case | WP Content (What shall be done?) - Print the Case |  |  |
|  | WP Result (What is achieved after WP was finished?) - Having a ready to use case for the weather station - Combination with raspberry and other components |  |  |
|  | Progress Measurement (How is progress measured?) - Having a successful print - Making the other components fit |  |  |
| 2.6 Think about an Anemometer | WP Content (What shall be done?) - Think about an Anemometer |  |  |
|  | WP Result (What is achieved after WP was finished?) - Have an idea to build an Anemometer |  |  |
|  | Progress Measurement (How is progress measured?) - The concept can be implemented |  |  |
| 2.7 Combine the Anemomter and the Case | WP Content (What shall be done?) - Assemble the Anemometer and the Case |  |  |
|  | WP Result (What is achieved after WP was finished?) - The Raspberry Pi Zero can read the data of the anemometer |  |  |
|  | Progress Measurement (How is progress measured?) - The Data is displayed in the database |  |  |
| 3.1. Basic Framework | WP Content (What shall be done?) - Programming the Basic Framework of the Frontend |  |  |
|  | WP Result (What is achieved after WP was finished?) - Creating a functional running program |  |  |
|  | Progress Measurement (How is progress measured?) - If there are no errors - Program is running |  |  |
| 3.2. Website with not yet functional features | WP Content (What shall be done?) - Programming the website with the necessary features |  |  |
|  | WP Result (What is achieved after WP was finished?) - Having a not yet functional website |  |  |
|  | Progress Measurement (How is progress measured?) - Control and looking at the website |  |  |
| 3.3. Functionalities | WP Content (What shall be done?) - Programming the functionalities |  |  |
|  | WP Result (What is achieved after WP was finished?) - Sensor-data and printing it out |  |  |
|  | Progress Measurement (How is progress measured?) - If you can see the data on the website |  |  |
| 3.4. Design | WP Content (What shall be done?) - Design of the website Promotion cum laude zum Dr. med. dent. an der Semmelweis Universität Budapest |  |  |
|  | WP Result (What is achieved after WP was finished?) - Having a well looking website |  |  |
|  | Progress Measurement (How is progress measured?) - Adding simple elements |  |  |
| 4.1. Database | WP Content (What shall be done?) - Setup a small database to save |  |  |
|  | WP Result (What is achieved after WP was finished?) - Having a well modeld Database |  |  |
|  | Progress Measurement (How is progress measured?) - Values can be stored effectively |  |  |
| 4.2. APIs | WP Content (What shall be done?) - Coding APIs |  |  |
|  | WP Result (What is achieved after WP was finished?) - Frontend can reach Data |  |  |
|  | Progress Measurement (How is progress measured?) - Values are displayed on the Frontend |  |  |
| 4.3. Web Server | WP Content (What shall be done?) - Setting up a web server |  |  |
|  | WP Result (What is achieved after WP was finished?) - A web server is running |  |  |
|  | Progress Measurement (How is progress measured?) - The website that displays the data can be accessed |  |  |

## Project Responsibility Matrix

| Wetterstation 001 |  | PROJECT- RESPONSIBILITY- MATRIX |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| WBS-Code | Roles & Environment WP-Title |  | External project owner | Project owner | Project manager | Project assistant | Project team member 1 | Project team member 2 | Project team member 3 | Project team member 4 | Project team member 5 |  | Project member 1 | Project member 2 | Project member 3 | Project coach |
| 1.0 | Project Management |  |  | I | R |  | C | C |  |  |  |  |  |  |  |  |
| 1.0.1 | Define goals for Project |  |  | I | R |  | C | C |  |  |  |  |  |  |  |  |
| 1.0.2 | Write Project-Handbook |  |  | I | R |  | C | C |  |  |  |  |  |  |  |  |
| 1.0.3 | Kick-off meeting |  |  | I | R |  | C | C |  |  |  |  |  |  |  |  |
| 1.1 | Hardware |  |  | I | C |  | I | R |  |  |  |  |  |  |  |  |
| 1.1.1 | Set up the Raspberry Pi Zero 2W |  |  | I | I |  | I | R |  |  |  |  |  |  |  |  |
| 1.1.1.1 | Put an OS on the Raspberry Pi Zero |  |  | I | I |  | I | R |  |  |  |  |  |  |  |  |
| 1.1.1.2 | Use correct resistors and sensors |  |  | I | I |  | I | R |  |  |  |  |  |  |  |  |
| 1.1.1.3 | Read out sensors |  |  | I | C |  | I | R |  |  |  |  |  |  |  |  |
| 1.1.2 | Case modeling |  |  | I | I |  | I | R |  |  |  |  |  |  |  |  |
| 1.1.3 | Build Anemometer |  |  | I | I |  | I | R |  |  |  |  |  |  |  |  |
| 1.1.3.1 | Connect the Anemometer |  |  | I | I |  | I | R |  |  |  |  |  |  |  |  |
| 1.2 | Backend |  |  | I | R |  | C | C |  |  |  |  |  |  |  |  |
| 1.2.1 | Set up a database |  |  | I | R |  | I | C |  |  |  |  |  |  |  |  |
| 1.2.1.1 | Get Sensor Data |  |  | I | R |  | I | C |  |  |  |  |  |  |  |  |
| 1.2.1.2 | Insert in data in database |  |  | I | R |  | I | C |  |  |  |  |  |  |  |  |
| 1.2.2 | Create APIs |  |  | I | R |  | C | I |  |  |  |  |  |  |  |  |
| 1.2.2.1 | Code APIs |  |  | I | R |  | I | I |  |  |  |  |  |  |  |  |
| 1.2.2.2 | Implement in Frontend |  |  | I | C |  | R | I |  |  |  |  |  |  |  |  |
| 1.2.3 | Set up a web server |  |  | I | R |  | C | I |  |  |  |  |  |  |  |  |
| 1.2.3.1 | Frontend displays |  |  | I | R |  | C | I |  |  |  |  |  |  |  |  |
| 1.2.3.2 | Web server is reachable |  |  | I | R |  | I | I |  |  |  |  |  |  |  |  |
| 1.3 | Frontend |  |  | I | I |  | R | I |  |  |  |  |  |  |  |  |
| 1.3.1 | Creating the Framework of the website |  |  | I | I |  | R | I |  |  |  |  |  |  |  |  |
| 1.3.2 | Make it well looking |  |  | I | I |  | R | I |  |  |  |  |  |  |  |  |
| 1.3.3 | Implement the functions |  |  | I | C |  | R | I |  |  |  |  |  |  |  |  |

Functions

R …….Responsible

C …….Contribution

I ……..has to be informed

## Milestoneplan

| Wetterstation 001 |  | MILESTONEPLAN |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| WBS-Code | Milestone |  | Plan date | Revised date |  | Actual date |
| 4 | Finished readable sensors |  | 12.02.2026 | 12.02.2026 |  | 12.02.2026 |
| 10 | Finished Web UI Foundation |  | 17.03.2026 | 17.03·2026 |  | 17.03·2026 |
| 7 | Finished case |  | 30.03.2026 |  |  |  |
| 16 | Finished Database and APIs |  | 26.03.2026 |  |  |  |
| 13 | Finished Fronted |  | 29.04.2026 |  |  |  |
| 18 | Finished Web Server |  | 15.05.2026 | 25.03.2026 |  | 25.03.2026 |
| 20 | Finished Project |  | 10.06.2026 |  |  |  |

*In order of plan dates.

## Project Bar Chart

## Resource Plan

| Wetterstation 001 |  |  | Resource Plan |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| WBS-Code | Phase/Work-package | Type of resource |  | Planned quantity (days) | Revised quantity (days) | Actual quantity (days) | Deviation (days) |
| 2 | Raspberry activation | Raspberry Pi Zero 2W, Laptop, Raspberry Pi Imager |  | 12 | 12 | 12 | 0 |
| 3 | Sensor implementation | Raspberry Pi Zero 2W, DHT22, BME280 |  | 12 | 12 | 12 | 0 |
| 6 | Think about an Anemometer | Raspberry Pi Zero 2W, Parts of an Anemometer |  | 5 | 5 | 5 | 0 |
| 7 | Build an Anemometer | Parts of an Anemometer |  | 10 | 10 | 10 | 0 |
| 5 | Case modeling and printing | 3D-Printer, ABS- Filament, Laptop, Oneshape |  | 15 | 15 | 15 | 0 |
| 8 | Combine Anemometer and Case | Case, Anemometer |  | 10 |  |  |  |
| 10 | Framework for Web UI | Laptop, Virtual Studio Code |  | 10 | 10 | 10 | 0 |
| 11 | Web UI with not yet functional features | Laptop, Virtual Studio Code |  | 15 | 15 | 15 | 0 |
| 13 | Functionalities in Web UI | Laptop, Virtual Studio Code |  | 12 |  |  |  |
| 14 | Web UI Design | Laptop, Virtual Studio Code |  | 12 |  |  |  |
| 16 | Setup a Database | Laptop, Raspberry Pi Zero 2W, DataGrip |  | 15 | 15 | 15 | 0 |
| 17 | Creating APIs | Laptop, Raspberry Pi Zero 2W, Virtual Studio Code |  | 15 |  |  |  |
| 19 | Create Web Server | Laptop, Raspberry Pi Zero 2W, Virtual Studio Code |  | 12 | 12 | 12 | 0 |
| 21 | Setup mDNS | Laptop, Raspberry Pi Zero 2W, Virtual Studio Code |  | 12 |  |  |  |

## Project Cost Plan

| Wetterstation 001 |  | PROJECT COST PLAN |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| WBS-Code, WP-Title | Type of Cost |  | Planned cost | Revised cost | Actual cost |  | Deviation |
| 3 | - Personnel |  | 0€ |  |  |  |  |
|  | - Material |  | 98€ |  |  |  |  |
|  | - External services |  | 0€ |  |  |  |  |
|  | - Other |  | 0€ |  |  |  |  |
|  | Total |  | 98€ |  |  |  |  |
| Project cost |  |  | 98€ |  |  |  |  |

## Project Communication

| Wetterstation 001 |  | PROJECT- COMMUNICATION |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Title | Objectives, Content |  | Participants | Schedule | Location |
| Project owner meeting | - project status - decisions - acceptance of progress report |  | Project owner, Project manager | Not yet scheduled | Teacher Table |
| Project controlling meeting | - project status - controlling of tasks, schedule, resources, costs - controlling of project environments - social controlling - prepare proposal for decision |  | Project manager, Project team, Project coach | Every Monday at 11 o clock | Last Row, classroom T233 |
| Subteam meeting | - Coordination of subteams - Discussion of problems |  | Subteam | Every Monday at 11 o clock | Last Row, classroom T233 |

## Project „Rules“

Communication:

- Weekly Meetings: The participation of the Project Team Member and the Project Manager in the Weekly Meetings is very important. The meeting is scheduled every Monday at 11 o clock.

- File sharing: All files belonging to the project must be published in the GitHub repository. No other ways to share files are allowed.

- Communication channels: All important information will be published in the team group.

General Collaboration:

- Time Management: Each team member is responsible for their own work packages. These must be completed by the deadline. If more time is needed, this must be requested promptly.

- Support:

  - If help is needed with a work package, it must be requested promptly.

  - If someone needs help and you have the time and are able to help, you are obligated to do so.

Documentation:

- Version Control: The Project Handbook must be updated regularly. Significant changes require a new version number and an entry in the document history.

Technical Standard:

- Hardware Care: Care must be taken with the hardware components, and they must not be damaged or broken in any way. If this happens, the affected part must be replaced.

## Project Risk Analysis

|  |  | PROJECT RISK ANALYSIS |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| WBS- Code | WBS- description | Risk- description | Priority | Benefit /Cost | Probability | Risk- value | Delay | Avoiding action | Cost for minimizing risk |
| (Code) | (Text) | (Text) | (Range) | (iuro) | (Percentage) | (iuro) | (iWeeks) | (Text) | (Euro) |
| 2 | Raspberry activation | break | 1 | 30€ | 10% | 30€ | 1-2Weeks | Take Care | 0€ |
| 3 | Senor implementation | Sensor breaks | 1 | 5-10€ | 10% | 5-10€ | 1-2Weeks | Take Care | 0€ |
| 5 | Workout energy independent supply | Provide not enough electricity | 2 | 20€ | 20% | 20€ | 1-2Weeks | First Think, than buy | 15€ |
| 6 | Case Modeling | Wrong size | 4 | 5€ | 40% | 5€ | ½ Week | Measure correctly | 0€ |
| 14 | Setup a Database | Database is too small | 2 | 0€ | 10% | 0€ | ½ Week | Think first about the right size | 0€ |
| 15 | Creating APIs | APIs don’t share the data | 5 | 0€ | 15% | 0€ | ½ Week | Have a clear structure | 0€ |
| 17 | Create Web Server | The server don’t start | 3 | 0€ | 10% | 0€ | ½ Week | Inform you how to create a server | 0€ |
| 18 | setup mDNS | DNS doesn’t work | 3 | 0€ | 20% | 0€ | ½ Week | Inform you how to setup mDNS | 0€ |
| Project total |  |  |  |  |  |  |  |  |  |

## Project Documentation

| Area | Description |
| --- | --- |
| File | In the GitHub Repository: Directory named “Documentation” |
| Access Authorisation | Everyone from the Project Team has access to the documentation |
| Naming convention | DDMMYYYY_version_name.docx |
| Rules |  |

# Project Start

## Minutes– Project Start

### Project Start Workshop

### Follow-up Workshop

### Project Owner Meeting

# Project Co-ordination

## Approval of Work-packages

| Wetterstation 001 |  | APPROVAL OF WORK-PACKAGES |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| WBS-Code | Work-package |  | WP-Owner | Date | Approval by | Signature |
| 2 | Raspberry activation |  | Berbauer K. | 27.01.26 | Brückl M. | Brückl M. |
| 3 | Sensor implementation |  | Berbauer K. | 02.02.26 | Brückl M. | Brückl M. |
| 5 | Case Modeling |  | Berbauer K. | 19.04.26 | Brückl M. | Brückl M. |
| 6 | Think about an Anemometer |  | Berbauer K. | 25.03.26 | Brückl M. | Brückl M. |
| 7 | Build the Anemometer |  | Bergbauer K. |  |  |  |
| 10 | Framework for Web UI |  | Aistleitner D. | 10.03.26 | Brückl M. | Brückl M. |
| 11 | Web UI with not yet functional features |  | Aistleitner D. | 17.03.26 | Brückl M. | Brückl M. |
| 13 | Functionalities in Web UI |  | Aistleitner D. |  |  |  |
| 14 | Design |  | Aistleitner D. | 25.04.26 | Brückl M. | Brückl M |
| 16 | Setup a Database |  | Brückl M. | 15.03.26 | Brückl M. | Brückl M. |
| 17 | Creating APIs |  | Brückl M. |  |  |  |
| 19 | Create Web Server |  | Brückl M. | 11.03.36 | Brückl M. | Brückl M. |
| 21 | setup mDNS |  | Brückl M. |  |  |  |

## Minutes – Project Co-ordination

# Project Controlling

## Project Status Report

| Wetterstation 001 | PROJECT STATUS REPORT as of Bergbauer Klaus |  |  |  |
| --- | --- | --- | --- | --- |
| Project crisis Project in difficulties Project according to plan |  | - Overall Status: - The project is progressing well. Raspberry Pi Zero 2W has been successfully set up with SSH and Wi-Fi enabled. DHT11 sensor testing is underway, and the basic React website structure is complete. |  |  |
| 2) Status Project objectives - Set up Raspberry Pi Zero 2W with OS Lite - Enable remote access via SSH - Test DHT11 temperature/humidity sensor - Develop React-based web interface |  |  | Activities: - Raspberry Pi successfully configured - DHT11 sensor integrated and tested (command line output working) - Basic website structure implemented in React |  |
| 3) Status Project progress - Hardware setup: 80% complete (waiting for hardware shipment) - Sensor integration: 55% complete (testing phase) - Website development: 20% complete (structure done, output pending) |  |  | Activities: - Raspberry OS Lite installed on 32GB Micro SD card - SSH and Wi-Fi connectivity established - DHT11 sensor displaying data in terminal - React frontend Framework implemented |  |
| 4) Status Schedule - On track - all milestones met by 03.02.2026 - No delays reported |  |  | Activities: - Phase 1 (Hardware Setup) completed on time (with lend Raspberry) - WBS 3 (Sensor Testing) in progress as planned |  |
| 5) Status Resources/costs - Raspberry Pi Zero 2W (lended) - 32GB Micro SD card - DHT11 sensor (for testing) - DHT22 sensor - BMP280 |  |  | Activities: - Nearly all required hardware procured - Budget within limits - No additional resource requirements identified |  |
| 6) Status Context - Raspberry Pi Imager used for OS installation - PowerShell used for remote SSH connection |  |  | Activities: - Documentation of setup procedure completed - Network connectivity stable - No external blockers or dependencies |  |
| 7) Status Organisation/culture - Author: Klaus Bergbauer - Collaboration ongoing |  |  | Activities: - Knowledge sharing via progress documentation - Testing and development workflow established - Communication channels functional (SSH, Wi-Fi) |  |

## Project Status Report

| Wetterstation 001 | PROJECT STATUS REPORT as of Brückl Matthias |  |  |  |
| --- | --- | --- | --- | --- |
| Project crisis Project in difficulties Project according to plan |  | - Overall Status: - The project is progressing well. Raspberry Pi Zero 2W can readout the DHT22 and the BME280 sensors. The first steps towards a database have been taken and the Web User Interface has been optimized. |  |  |
| 2) Status Project objectives - Integrate high-precision sensors (DHT22, BME280) - Automate data retrieval via scripting - Improve React frontend design |  |  | Activities: - DHT22 & BME280 successfully wired and recognized - Custom script for data reading completed - UI styling and layout optimization finished |  |
| 3) Status Project progress - Hardware setup: 100% (All sensors arrived and installed) - Data Processing: 90% (Scripts functional) - Website development: 40% (UI refined) |  |  | Activities: - Replaced DHT11 with superior DHT22/BME280 sensors - Developed and debugged data collection script - Implemented CSS/styling updates to the React WebUI |  |
| 4) Status Schedule - On track - all milestones met by 16.02.2026 - No delays reported |  |  | Activities: - WP 2 (Raspberry activation) completed on time (with lend Raspberry) - WP 3 (Sensor implementation) completed |  |
| 5) Status Resources/costs - Raspberry Pi Zero 2W (lended) - 32GB Micro SD card - DHT22 sensor - BME280 |  |  | Activities: - Nearly all required hardware procured - Budget within limits - No additional resource requirements identified |  |
| 6) Status Context - PowerShell used for remote SSH connection - Python Scripts used to read out the sensors - data output verified via terminal |  |  | Activities: - Documented the pinout configuration for the new sensors - No external blockers or dependencies |  |
| 7) Status Organisation/culture - Author: Matthias Brückl - Collaboration ongoing - Documentation updated for new hardware |  |  | Activities: - Knowledge sharing via progress documentation - Testing and development workflow established - new Scripts are published to the other Projektmembers |  |

## Project Status Report

| Wetterstation 001 | PROJECT STATUS REPORT as of Aistleitner Daniel |  |  |  |
| --- | --- | --- | --- | --- |
| Project crisis Project in difficulties Project according to plan |  | - Overall Status: - The project is progressing well. Work on the system architecture has expanded. We have successfully started the database initialization and the independent power concept, necessitating an earlier setup of the web server for performance monitoring. |  |  |
| 2) Status Project objectives - Worked out a concept for an independent power supply - Write a logging script - created a web server on the Raspberry Pi |  |  | Activities: - Concept design for solar/battery power integration - Development of a logging strategy for system stability - Initial web server deployment |  |
| 3) Status Project progress - WP5 (Work out energy independent power supply) completed - WP14 (Setup a Database) is 95% finished - WP9 (Web UI with not yet functional features) is 75% finished |  |  | Activities: - Research and component selection for the independent power supply - An Apache Web Server was installed on the Raspberry Pi - Setup an SQLite Database |  |
| 4) Status Schedule - On track - minimal delays reported - The web server setup was pulled forward from WP 17 to analyze system load early |  |  | Activities: - all milestones are almost reached by 11.03.2026 |  |
| 5) Status Resources/costs - Raspberry Pi Zero 2W (lended) - 32GB Micro SD card - DHT22 sensor - BME280 |  |  | Activities: - Budget within limits - Solar panel and batteries are being ordered |  |
| 6) Status Context - Used Python for the logging script and SQL to build a database - Used the Apache services for the web server |  |  | Activities: - The scripts were documented with comments - documented all commands for the installation of the web services |  |
| 7) Status Organisation/culture - Author: Matthias Brückl - Collaboration ongoing - Documentation updated |  |  | Activities: - Knowledge sharing via progress documentation |  |

## Project Status Report

| Wetterstation 001 | PROJECT STATUS REPORT as of Brückl M. |  |  |  |
| --- | --- | --- | --- | --- |
| Project crisis Project in difficulties Project according to plan |  | - Overall Status: - The project is progressing well. The backend foundation has been finalized: a main.py entry point and a systemd daemon on the Raspberry Pi have been set up to automatically start the backend. The database initialization script is now complete. The frontend has been redesigned with a dashboard-style layout. A hardware change was made: solar power has been dropped in favor of an anemometer for wind speed measurement. Power supply concepts using a battery have been considered. |  |  |
| 2) Status Project objectives - Set up main.py as system entry point and configure systemd daemon - Finalize database initialization script (init_db.py) - Redesign frontend with a dashboard-style layout - Replace solar power with anemometer for wind speed measurement - Evaluate battery-based power supply concept |  |  | Activities: - main.py created with logging and DB initialization on startup - Systemd daemon configured to auto-start backend on Raspberry Pi boot - init_db.py finalized: tables, indices, and seed data completed - Frontend redesigned as a dashboard with improved data visualization |  |
| 3) Status Project progress - WP14 (Setup a Database): 100% complete - WP9 (Web UI with not yet functional features): 100% complete - WP5 (Energy independent power supply): concept revised, solar dropped |  |  | Activities: - Database init script fully implemented and tested - New dashboard layout deployed on frontend - Hardware concept updated: anemometer added, solar panel removed |  |
| 4) Status Schedule - On track. No significant delays. |  |  | Activities: - WP8 (Framework for Web UI) completed - WP9 (Web UI with not yet functional features) completed - WP14 (Setup a Database) completed |  |
| 5) Status Resources/costs - Budget within limits. Anemometer to be ordered. |  |  | Activities: - Budget within limits - Solar panel dropped from requirements - Anemometer to be ordered |  |
| 6) Status Context - Python (backend) - SQLite - React + TypeScript (frontend) |  |  | Activities: - Backend scripts documented with comments - Dashboard layout implemented in React - Systemd service file created for auto-start |  |
| 7) Status Organisation/culture - Author: Matthias Brückl. - Collaboration ongoing. - Documentation updated. |  |  | Activities: - Knowledge sharing via progress documentation - New scripts published to project members via GitHub |  |

## Project Status Report

| Wetterstation 001 | PROJECT STATUS REPORT as of Bergbauer K. |  |  |  |
| --- | --- | --- | --- | --- |
| Project crisis Project in difficulties Project according to plan |  | - Overall Status: - The project is progressing well. Parts for the self-built anemometer have been researched and ordered. The folder structure on the Raspberry Pi has been reorganized for better maintainability. The frontend development has been continued and the Project Handbook has been updated to reflect the hardware change from solar power to an anemometer. |  |  |
| 2) Status Project objectives - Research and order parts for a self-built anemometer - Reorganize folder structure on Raspberry Pi - Continue frontend development |  |  | Activities: - Identified required components for the anemometer and placed the order - Revised and cleaned up the directory structure on the Raspberry Pi - Continued work on the website frontend |  |
| 3) Status Project progress - WP6 (Think about an Anemometer): 100% complete - WP7 (Build the Anemometer): 10% (parts ordered, awaiting delivery) - WP13 (Functionalities in Web UI): in progress - WP14 (Web UI Design): in progress |  |  | Activities: - Anemometer parts sourced and ordered - Raspberry Pi file system restructured for cleaner project layout - Frontend development ongoing |  |
| 4) Status Schedule - On track. No significant delays. |  |  | Activities: - WP6 (Think about an Anemometer) completed - on time Parts for WP7 ordered as planned |  |
| 5) Status Resources/costs - Budget within limits. Anemometer is ordered |  |  | Activities: - Budget within limits - Anemometer components ordered - Solar panel removed from requirements |  |
| 6) Status Context - React + TypeScript (frontend) - Raspberry Pi Zero 2W |  |  | Activities: - Frontend continued to be developed on local machine |  |
| 7) Status Organisation/culture - Author: Bergbauer Klaus - Collaboration ongoing. - Documentation updated. |  |  | Activities: - Knowledge sharing via progress documentation |  |

## Project Status Report

| Wetterstation 001 | PROJECT STATUS REPORT as of Bergbauer K. |  |  |  |
| --- | --- | --- | --- | --- |
| Project crisis Project in difficulties Project according to plan |  | - Overall Status: - The project is progressing steadily. This week was focused on hardware preparation. The ordered anemometer parts have arrived and been received. The components intended for 3D printing have been commissioned. Additionally, work on the 3D modeling of the housing has begun using Tinkercad. |  |  |
| 2) Status Project objectives - Receive and inspect ordered anemometer parts - Commission 3D-printable components - Begin 3D modeling of the weather station case |  |  | Activities: - Anemometer parts received and inspected Components to be 3D-printed have been commissioned - Started 3D design of the case in Tinkercad |  |
| 3) Status Project progress - WP7 (Build the Anemometer): 20% (parts received, assembly pending) - WP5 (Case Modeling): 15% (3D model started in Tinkercad) - WP8 (Print Case): 5% (print job commissioned) |  |  | Activities: - Anemometer components checked for completeness 3D printing order placed for required parts Initial case geometry drafted in Tinkercad |  |
| 4) Status Schedule - On track. No significant delays. |  |  | Activities: - Parts arrived as expected 3D modeling started on schedule |  |
| 5) Status Resources/costs - Budget within limits. |  |  | Activities: - Budget within limits All required anemometer parts received 3D print material (ABS) in use |  |
| 6) Status Context - Tinkercad used for 3D modeling Anemometer parts on hand |  |  | Activities: - 3D model being developed locally in Tinkercad - Components organized and stored properly |  |
| 7) Status Organisation/culture - Author: Aistleitner Daniel - Collaboration ongoing. - Documentation updated. |  |  | Activities: - Knowledge sharing via progress documentation Updates shared with project team via GitHub |  |

## Project Status Report

| Wetterstation 001 | PROJECT STATUS REPORT as of Brückl M. |  |  |  |
| --- | --- | --- | --- | --- |
| Project crisis Project in difficulties Project according to plan |  | - Overall Status: - The project is progressing well. The 3D-printed components for the anemometer have arrived and assembly can now begin. Work on the case design has been started. API development has been initiated to connect the backend with the frontend. The web interface has been further developed. |  |  |
| 2) Status Project objectives - Receive 3D-printed anemometer components and prepare assembly - Start drawing/designing the weather station case - Begin API development - Continue web interface development |  |  | Activities: - 3D-printed parts for the anemometer received and ready for assembly - Case design work started - API development initiated - Web UI further developed and improved |  |
| 3) Status Project progress - WP7 (Build the Anemometer): 60% (3D parts received, assembly pending) - WP5 (Case Modeling): 30% (design started) - WP17 (Creating APIs): 20% (development initiated) - WP13/14 (Web UI Functionalities & Design): in progress |  |  | Activities: - Anemometer assembly preparation underway - Case geometry being designed - First API endpoints being coded - Frontend continued to be developed |  |
| 4) Status Schedule - On track. No significant delays. |  |  | Activities: - All work packages progressing as planned |  |
| 5) Status Resources/costs - Budget within limits. |  |  | Activities: - No additional costs incurred |  |
| 6) Status Context - React + TypeScript (frontend) - Python (backend/APIs) - Tinkercad (case design) |  |  | Activities: - Development ongoing on local machines and loan Raspberry Pi Zero 2W |  |
| 7) Status Organisation/culture - Author: Brückl M. - Collaboration ongoing. - Documentation updated. |  |  | Activities: - Updates shared with project team via GitHub |  |

## Project Status Report

| Wetterstation 001 | PROJECT STATUS REPORT as of Bergbauer K. |  |  |  |
| --- | --- | --- | --- | --- |
| Project crisis Project in difficulties Project according to plan |  | - Overall Status: - The project is progressing well and according to plan. A major technical milestone was reached by configuring the Raspberry Pi to create its own hotspot for WLAN configuration when no network is available. The hardware phase has moved into physical testing with the first test prints of the case and the start of the anemometer assembly. Software development is also on track with the addition of a settings window to the web interface and continued API development. The team successfully received the Raspberry Pi Zero 2W. |  |  |
| 2) Status Project objectives - Implement a hotspot mode on the Raspberry Pi for easy WLAN setup. - Continue case modeling and evaluate initial test prints. - Expand the web interface with a dedicated settings window. - Advance the development of backend APIs. - Start the physical assembly of the anemometer. |  |  | Activities: - Raspberry Pi hotspot mode configured and tested - First test prints of the case completed and evaluated - Settings window added to the web interface - API development continued and expanded - Raspberry Pi Zero 2W received by the team - Anemometer assembly started |  |
| 3) Status Project progress - WP7 (Build the Anemometer): 70% (assembly started) - WP5 (Case Modeling): 45% (first test prints completed) - WP17 (Creating APIs): 40% (development ongoing) - WP13/14 (Web UI Functionalities & Design): in progress (settings window added) |  |  | Activities: - Hotspot functionality implemented on Raspberry Pi - Initial case test prints reviewed and assessed - Settings window integrated into the web interface - Additional API endpoints developed - Own Raspberry Pi Zero 2W received and set up - Anemometer physical assembly begun |  |
| 4) Status Schedule - On track. No significant delays. |  |  | Activities: - All work packages progressing as planned |  |
| 5) Status Resources/costs - Budget within limits. |  |  | Activities: - No additional costs incurred |  |
| 6) Status Context - React + TypeScript (frontend / web interface) - Python (backend / APIs) - Tinkercad / CAD tool (case modeling) - Raspberry Pi Zero 2W (own hardware) |  |  | Activities: - Hotspot configuration documented - Test print results evaluated and recorded - Development ongoing on local machines and own Raspberry Pi Zero 2W |  |
| 7) Status Organisation/culture - Author: Bergbauer K. - Collaboration ongoing. - Documentation updated. |  |  | Activities: - Updates shared with project team via GitHub |  |

## Additional Project Status Reports

## Minutes – Project controlling

### Project Controlling Meetings

### Project Owner Meetings

# Project Close Down

## Project Close Down Report

| Wetterstation 001 |  | PROJECT CLOSE DOWN REPORT |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| - Overall impression |  |  | - Reflection: Fulfilment of objectives |  |  |  |  |
| - Reflection: Deliverables / Schedule |  |  |  |  |  |  |  |
| - Reflection: Resources / Costs |  |  |  |  |  |  |  |
| - Reflection: Internal Organisation / Environmental Relationships |  |  |  |  |  |  |  |
| - Performance appraisal (Project owner, Project manager, Project member) |  |  | - Lessons learned (Summary of Experiences and suggestions for improvement) |  |  |  |  |
| - Post-Project Phase Planning, Additional Tasks |  |  |  |  |  |  |  |
|  | To-Do |  |  | Owner |  | Schedule |  |
| - Project Close Down HTL Wels (Project owner) Brückl Matthias (Project manager) |  |  |  |  |  |  |  |

## Minutes – Project Close Down

### Project Close Down Workshop